## Planning Parameters
Planning Horizon | 3 | (note: iteration length = 1 month)
Capacity (man-hours) | 40
Investment Horizon | 12
Discount rate | 2%
Budget (£1,000) | 30

## Backlog & dependencies
Work Items | Dependencies
A. View council tax bills | 1. Sign up and login | 2. Interface to residents repository
B. Apply for council tax reduction | 1. Sign up and login | 2. Interface to residents repository
C. Pay council tax | 3. Payment processor | A. View council tax bills
D. View council tax reduction claim | B. Apply for council tax reduction
E. report house move | 1. Sign up and login | 2. Interface to residents repository
F. apply for parking permit | 1. Sign up and login | 2. Interface to residents repository | 3. Payment processor
G. Buy visitor parking permit | 1. Sign up and login | 2. Interface to residents repository | 3. Payment processor
H. Pay parking and traffic fine | 3. Payment processor | 6. Interface to parking fine system
I. Look up rubbish collection day | 4. Interface to rubbish collection system
J. Report missed rubbish collection | 2. Interface to residents repository | 4. Interface to rubbish collection system
K. Order recycling bin | 1. Sign up and login | 4. Interface to rubbish collection system
L. Submit housing application | 5. Interface to Council Housing Repository
M. Report accommodation problem | 5. Interface to Council Housing Repository
N. Submit planning application | 3. Payment processor
O. Comment on planning application | 1. Sign up and login
P. Create application alert | N. Submit planning application
Q. View planning applications
R. Contest parking fines | 6. Interface to parking fine system
S. set up council tax direct debit
1. Sign up and login
2. Interface to residents repository
3. Payment processor
4. Interface to rubbish collection system
5. Interface to Council Housing Repository
6. Interface to parking fine system

## Effort Estimates
Work Items | Lower Limit | Lower Quartile | Median | Upper Quartile | Upper Limit | Fitted Mu | Fitted Sigma
A. View council tax bills | 1 | 4 | 5 | 10 | 30 | 1.747 | 0.73
B. Apply for council tax reduction | 1 | 8 | 15 | 20 | 40 | 2.61 | 0.65
C. Pay council tax | 1 | 4 | 7 | 10 | 20 | 1.88 | 0.64
D. View council tax reduction claim | 1 | 4 | 5 | 10 | 30 | 1.747 | 0.73
E. report house move | 1 | 7 | 10 | 18 | 30 | 2.35 | 0.65
F. apply for parking permit | 1 | 8 | 15 | 20 | 40 | 2.61 | 0.65
G. Buy visitor parking permit | 1 | 5 | 10 | 15 | 30 | 2.21 | 0.75
H. Pay parking and traffic fine | 1 | 5 | 11 | 22 | 30 | 2.32 | 0.88
I. Look up rubbish collection day | 1 | 4 | 8 | 12 | 20 | 1.98 | 0.71
J. Report missed rubbish collection | 1 | 4 | 8 | 12 | 20 | 1.98 | 0.71
K. Order recycling bin | 1 | 4 | 8 | 12 | 20 | 1.98 | 0.71
L. Submit housing application | 4 | 8 | 15 | 20 | 40 | 2.61 | 0.65
M. Report accommodation problem | 1 | 4 | 8 | 12 | 20 | 1.98 | 0.71
N. Submit planning application | 4 | 15 | 20 | 25 | 60 | 2.98 | 0.38
O. Comment on planning application | 2 | 5 | 8 | 12 | 20 | 2.05 | 0.59
P. Create application alert | 1 | 3 | 4 | 5 | 10 | 1.37 | 0.38
Q. View planning applications | 1 | 3 | 4 | 5 | 10 | 1.37 | 0.38
R. Contest parking fines | 1 | 5 | 10 | 15 | 30 | 2.21 | 0.75
S. set up council tax direct debit | 1 | 2 | 4 | 6 | 10 | 1.3 | 0.69
1. Sign up and login | 1 | 5 | 8 | 12 | 20 | 2.05 | 0.59
2. Interface to residents repository | 2 | 10 | 14 | 18 | 30 | 2.61 | 0.42
3. Payment processor | 1 | 8 | 12 | 16 | 30 | 2.45 | 0.5
4. Interface to rubbish collection system | 2 | 10 | 14 | 18 | 30 | 2.61 | 0.42
5. Interface to Council Housing Repository | 2 | 10 | 14 | 18 | 30 | 2.61 | 0.42
6. Interface to parking fine system | 2 | 10 | 14 | 18 | 30 | 2.61 | 0.42
251
| All estimates are in man-days |  |  |  |  | http://optics.eee.nottingham.ac.uk/match/uncertainty.php

## Value Estimates
Work Items | savings per online use (in pounds) | nbr of use before online | Lower Limit | Lower Quartile | Median | Upper Quartile | Upper Limit | Fitted Mu | Fitted Sigma
A. View council tax bills | 5 | 3000 | 0 | 5 | 15 | 25 | 50 | 2.51 | 1.04
B. Apply for council tax reduction | 25 | 1000 | 0 | 10 | 25 | 30 | 50 | 2.97 | 0.75
C. Pay council tax | 5 | 3000 | 0 | 5 | 15 | 25 | 50 | 2.51 | 1.04
D. View council tax reduction claim | 30 | 500 | 0 | 5 | 15 | 30 | 50 | 2.97 | 0.75
E. report house move | 30 | 500 | 0 | 5 | 15 | 25 | 50 | 2.51 | 1.04
F. apply for parking permit | 30 | 1000 | 0 | 20 | 30 | 50 | 100 | 3.42 | 0.65
G. Buy visitor parking permit | 20 | 2000 | 0 | 20 | 40 | 50 | 100 | 3.55 | 0.67
H. Pay parking and traffic fine | 20 | 1000 | 0 | 10 | 20 | 50 | 100 | 3.02 | 1.05
I. Look up rubbish collection day | 5 | 2000 | 0 | 5 | 10 | 15 | 50 | 2.22 | 0.82
J. Report missed rubbish collection | 15 | 500 | 0 | 5 | 7.5 | 15 | 50 | 2.09 | 0.82
K. Order recycling bin | 15 | 1000 | 0 | 5 | 15 | 25 | 50 | 2.51 | 1.04
L. Submit housing application | 50 | 500 | 0 | 10 | 25 | 50 | 100 | 3.13 | 1.03
M. Report accommodation problem | 15 | 1000 | 0 | 10 | 15 | 25 | 50 | 2.73 | 0.65
N. Submit planning application | 50 | 500 | 0 | 10 | 25 | 40 | 150 | 3.09 | 1.02
O. Comment on planning application | 15 | 1600 | 0 | 20 | 24 | 50 | 100 | 3.33 | 0.71
P. Create application alert | 5 | 1000 | 0 | 3 | 5 | 10 | 50 | 1.66 | 0.9
Q. View planning applications | 15 | 2000 | 0 | 20 | 30 | 50 | 100 | 3.42 | 0.65
R. Contest parking fines | 50 | 100 | 0 | 3 | 5 | 10 | 50 | 1.66 | 0.9
S. set up council tax direct debit | 10 | 1000 | 0 | 2 | 10 | 30 | 50 | 2.05 | 1.59
All estimates in 1,000 GBP per month
https://opendata.camden.gov.uk/
Nbr of residetns | 250000
Households estimates | 97000
Households with a car | 40000
Births per year | 2600
Deaths per year | 1200

## BEARS input
Work Item | Mean | SD | Mean | SD | Precedence
A | 1.747 | 0.73 | 2.51 | 1.04 | 1,2
B | 2.61 | 0.65 | 2.97 | 0.75 | 1,2
C | 1.88 | 0.64 | 2.51 | 1.04 | A,3
D | 1.747 | 0.73 | 2.97 | 0.75 | B
E | 2.35 | 0.65 | 2.51 | 1.04 | 1,2
F | 2.61 | 0.65 | 3.42 | 0.65 | 1,2,3
G | 2.21 | 0.75 | 3.55 | 0.67 | 1,2,3
H | 2.32 | 0.88 | 3.02 | 1.05 | 3,6
I | 1.98 | 0.71 | 2.22 | 0.82 | 4
J | 1.98 | 0.71 | 2.09 | 0.82 | 2,4
K | 1.98 | 0.71 | 2.51 | 1.04 | 1,4
L | 2.61 | 0.65 | 3.13 | 1.03 | 5
M | 1.98 | 0.71 | 2.73 | 0.65 | 5
N | 2.98 | 0.38 | 3.09 | 1.02 | 3
O | 2.05 | 0.59 | 3.33 | 0.71 | 1
P | 1.37 | 0.38 | 1.66 | 0.9 | N
Q | 1.37 | 0.38 | 3.42 | 0.65
R | 2.21 | 0.75 | 1.66 | 0.9 | 6
S | 1.3 | 0.69 | 2.05 | 1.59
1 | 2.05 | 0.59 | 0 | 0
2 | 2.61 | 0.42 | 0 | 0
3 | 2.45 | 0.5 | 0 | 0
4 | 2.61 | 0.42 | 0 | 0
5 | 2.61 | 0.42 | 0 | 0
6 | 2.61 | 0.42 | 0 | 0